HOSPITAL MANAGEMENT ERP

Phase-Wise Implementation Plan

Spring Boot | PostgreSQL | Microservices

Version 1.0

April 2026

Prepared by: Siance Software

CONFIDENTIAL

# Table of Contents

# 1. Introduction

## 1.1 Purpose

This document is the definitive implementation plan for the Hospital Management ERP (HM-ERP) system. It translates the functional requirements from the Comprehensive System Documentation into a concrete, phase-wise technical execution roadmap using Spring Boot, PostgreSQL, and a microservices architecture.

The plan covers microservice decomposition, database schemas per service, API contracts, infrastructure design, CI/CD pipelines, sprint-level task breakdowns, team structure, and risk mitigation strategies.

## 1.2 Reference Documents

- Hospital Management ERP - Comprehensive System Documentation v1.0

- Spring Boot Reference Documentation (3.3.x)

- PostgreSQL 16 Documentation

- HL7 FHIR R4 Implementation Guide

- HAPI FHIR Server Documentation

## 1.3 Technology Stack Overview

| Layer | Technology | Version | Purpose |
| --- | --- | --- | --- |
| Language | Java | 21 (LTS) | Primary development language with virtual threads support |
| Framework | Spring Boot | 3.3.x | Microservice framework with Spring Cloud ecosystem |
| Database | PostgreSQL | 16.x | Primary relational database per microservice |
| Cache | Redis | 7.x | Distributed caching, session store, pub/sub |
| Message Broker | Apache Kafka | 3.7.x | Async event-driven communication between services |
| Search | Elasticsearch | 8.x | Full-text search (patient, drug, diagnosis search) |
| Object Storage | MinIO / S3 | Latest | Document, image, and DICOM file storage |
| API Gateway | Spring Cloud Gateway | 4.1.x | Request routing, rate limiting, auth |
| Service Discovery | Spring Cloud Consul / Eureka | Latest | Service registration and discovery |
| Config Management | Spring Cloud Config | Latest | Centralized configuration server |
| Auth | Keycloak | 24.x | Identity and access management, SSO, RBAC |
| Containerization | Docker | 25.x | Service containerization |
| Orchestration | Kubernetes | 1.29.x | Container orchestration, scaling, service mesh |
| CI/CD | Jenkins / GitHub Actions | Latest | Build, test, deploy automation |
| Monitoring | Prometheus + Grafana | Latest | Metrics collection and visualization |
| Logging | ELK Stack (Elastic, Logstash, Kibana) | 8.x | Centralized logging and analysis |
| Tracing | Jaeger / Zipkin | Latest | Distributed request tracing |
| FHIR Server | HAPI FHIR | 7.x | HL7 FHIR R4 compliance layer |
| Frontend | React / Angular (recommended) | Latest | SPA frontend (separate repository) |

# 2. Microservice Architecture

## 2.1 Service Decomposition Strategy

Services are decomposed following Domain-Driven Design (DDD) principles. Each microservice owns its bounded context, has its own PostgreSQL database (database-per-service pattern), and communicates via REST APIs (synchronous) and Kafka events (asynchronous).

## 2.2 Complete Service Catalog

| Service Name | Bounded Context | Port | Database | Phase |
| --- | --- | --- | --- | --- |
| hm-gateway | API Gateway & routing | 8080 | None (stateless) | 1 |
| hm-auth-service | Authentication & authorization via Keycloak | 8081 | keycloak_db | 1 |
| hm-config-server | Centralized configuration | 8888 | Git repo | 1 |
| hm-discovery-server | Service registry | 8761 | None (in-memory) | 1 |
| hm-patient-service | Patient registration, MPI, demographics | 8100 | patient_db | 1 |
| hm-appointment-service | Scheduling, tokens, queue management | 8101 | appointment_db | 1 |
| hm-opd-service | OPD consultation, prescriptions, clinical notes | 8102 | opd_db | 1 |
| hm-billing-service | Charge capture, invoicing, payments | 8103 | billing_db | 1 |
| hm-master-data-service | ICD codes, drug master, service catalog | 8104 | master_db | 1 |
| hm-notification-service | SMS, email, push, WhatsApp notifications | 8105 | notification_db | 1 |
| hm-ipd-service | Admission, bed mgmt, discharge, nursing | 8200 | ipd_db | 2 |
| hm-emergency-service | ER triage, trauma, rapid workflows | 8201 | emergency_db | 2 |
| hm-lab-service | LIS - orders, samples, results, QC | 8202 | lab_db | 2 |
| hm-radiology-service | RIS - imaging orders, reports, DICOM | 8203 | radiology_db | 2 |
| hm-pharmacy-service | Drug dispensing, formulary, narcotics | 8204 | pharmacy_db | 2 |
| hm-nursing-service | Vitals, MAR, care plans, assessments | 8205 | nursing_db | 2 |
| hm-ot-service | OT scheduling, surgical safety, anesthesia | 8206 | ot_db | 2 |
| hm-inventory-service | Procurement, stock, GRN, vendor mgmt | 8300 | inventory_db | 3 |
| hm-hr-service | Employee, attendance, leave, payroll | 8301 | hr_db | 3 |
| hm-bloodbank-service | Donor, collection, testing, cross-match, issue | 8302 | bloodbank_db | 3 |
| hm-dietary-service | Diet plans, kitchen, meal tracking | 8303 | dietary_db | 3 |
| hm-insurance-service | TPA, pre-auth, claims, settlement | 8400 | insurance_db | 4 |
| hm-quality-service | Incidents, CAPA, infection control, accreditation | 8401 | quality_db | 4 |
| hm-analytics-service | Reports, dashboards, BI, data warehouse | 8402 | analytics_db (read replica) | 4 |
| hm-patient-portal | Patient-facing portal API | 8403 | Shares patient_db (read) | 4 |
| hm-fhir-service | FHIR R4 facade for interoperability | 8404 | fhir_db (HAPI) | 4 |

## 2.3 Inter-Service Communication Patterns

| Pattern | When to Use | Implementation |
| --- | --- | --- |
| Synchronous REST | Query another service for immediate data (e.g., patient lookup) | Spring WebClient / OpenFeign with circuit breaker (Resilience4j) |
| Async Events (Kafka) | State changes that other services react to (e.g., patient admitted) | Spring Kafka with Avro/JSON schema registry |
| Saga Pattern | Distributed transactions (e.g., billing + pharmacy + inventory) | Orchestration-based saga via a saga coordinator service |
| CQRS | High-read/low-write scenarios (e.g., analytics, dashboards) | Separate read models populated via Kafka consumers |
| Event Sourcing | Audit-critical flows (e.g., medication administration) | Event store per service, materialized views for queries |
| API Composition | Aggregate data from multiple services for UI | BFF (Backend for Frontend) in gateway layer |

## 2.4 Shared Libraries

Common functionality is extracted into shared Maven libraries to avoid code duplication:

| Library | Contents | Maven Artifact |
| --- | --- | --- |
| hm-common | Base DTOs, exception handling, pagination, audit annotations | com.siance.hm:hm-common |
| hm-security | JWT filter, RBAC annotations, Keycloak integration | com.siance.hm:hm-security |
| hm-kafka-common | Event DTOs, Kafka config, dead letter queue handling | com.siance.hm:hm-kafka-common |
| hm-audit | Audit logging aspect, audit trail entity, Kafka audit publisher | com.siance.hm:hm-audit |
| hm-fhir-mapper | FHIR R4 resource mappers (Patient, Encounter, Observation) | com.siance.hm:hm-fhir-mapper |

# 3. Project Structure and Conventions

## 3.1 Repository Strategy

Each microservice lives in its own Git repository within a single GitHub/GitLab organization. A parent BOM (Bill of Materials) repository manages dependency versions across all services.

| Repository | Purpose |
| --- | --- |
| hm-bom | Parent POM with dependency management, plugin versions, shared profiles |
| hm-common-libs | Multi-module project for shared libraries (hm-common, hm-security, etc.) |
| hm-patient-service | Patient registration microservice |
| hm-{service-name} | One repository per microservice (26 total) |
| hm-infra | Kubernetes manifests, Helm charts, Terraform scripts, Docker Compose files |
| hm-frontend | React/Angular SPA frontend application |
| hm-docs | Architecture decisions (ADRs), API documentation, runbooks |

## 3.2 Standard Service Structure

Every microservice follows this standard Maven project layout:

hm-patient-service/

pom.xml

Dockerfile

src/main/java/com/siance/hm/patient/

PatientServiceApplication.java

config/          (SecurityConfig, KafkaConfig, SwaggerConfig)

controller/      (PatientController, VisitController)

service/         (PatientService, VisitService)

repository/      (PatientRepository, VisitRepository)

entity/          (Patient, Visit, PatientContact, Allergy)

dto/             (PatientCreateDTO, PatientResponseDTO)

mapper/          (PatientMapper using MapStruct)

event/           (PatientRegisteredEvent, PatientUpdatedEvent)

exception/       (PatientNotFoundException, DuplicatePatientException)

validator/       (PatientValidator)

src/main/resources/

application.yml

application-dev.yml

application-prod.yml

db/migration/    (Flyway SQL migration scripts)

src/test/java/     (unit + integration tests)

## 3.3 Naming Conventions

| Element | Convention | Example |
| --- | --- | --- |
| Package | com.siance.hm.{service}.{layer} | com.siance.hm.patient.controller |
| Entity class | PascalCase, singular noun | Patient, Admission, LabOrder |
| Repository | {Entity}Repository | PatientRepository |
| Service | {Entity}Service / {Feature}Service | PatientService, TriageService |
| Controller | {Entity}Controller | PatientController |
| DTO | {Entity}{Action}DTO | PatientCreateDTO, PatientResponseDTO |
| Kafka Topic | hm.{service}.{event} | hm.patient.registered, hm.lab.result-validated |
| Database | {service}_db | patient_db, lab_db, billing_db |
| Table | Lowercase, snake_case, plural | patients, lab_orders, vital_signs |
| API Path | /api/v1/{resource} | /api/v1/patients, /api/v1/lab-orders |
| Flyway Migration | V{version}__{description}.sql | V1__create_patients_table.sql |

## 3.4 Key Spring Boot Dependencies (Common)

- spring-boot-starter-web - REST APIs

- spring-boot-starter-data-jpa - JPA/Hibernate for PostgreSQL

- spring-boot-starter-validation - Bean validation (Jakarta)

- spring-boot-starter-security - Security with Keycloak adapter

- spring-boot-starter-actuator - Health, metrics, info endpoints

- spring-kafka - Kafka producer/consumer

- springdoc-openapi-starter-webmvc-ui - Swagger/OpenAPI 3.0 docs

- flyway-core - Database migration

- mapstruct - DTO/Entity mapping

- resilience4j-spring-boot3 - Circuit breaker, retry, rate limiter

- spring-boot-starter-cache + spring-boot-starter-data-redis - Redis caching

- micrometer-registry-prometheus - Prometheus metrics export

- logstash-logback-encoder - JSON structured logging for ELK

# 4. Database Design (Per-Service Schemas)

## 4.1 Database-Per-Service Strategy

Each microservice owns its database exclusively. No direct cross-database queries are allowed. Data needed from other services is obtained via REST calls or event-driven replication (materialized views). Each database uses PostgreSQL with the following common features:

- UUID as primary key type (pg-uuid) for all entities

- Audit columns on every table: created_at, updated_at, created_by, updated_by

- Soft delete with deleted_at timestamp (nullable)

- Flyway-managed migrations with version control

- Row-level security (RLS) for multi-tenant deployments

- JSONB columns for extensible/dynamic attributes

- Full-text search using PostgreSQL tsvector for name/text searches

## 4.2 patient_db Schema

| Table | Key Columns | Indexes | Notes |
| --- | --- | --- | --- |
| patients | id (UUID PK), uhid (UNIQUE), first_name, last_name, dob, gender, blood_group, photo_url, national_id, status, metadata (JSONB) | uhid, national_id, phone_gin (trigram), name_tsvector | Master patient index; trigram index for fuzzy search |
| patient_contacts | id, patient_id (FK), type, value, is_primary, is_emergency | patient_id, value | Phone, email, emergency contacts |
| patient_addresses | id, patient_id (FK), type, line1, line2, city, state, country, pin_code, geo_point | patient_id, pin_code | PostGIS geo_point for location |
| patient_documents | id, patient_id (FK), doc_type, doc_number, issuing_authority, expiry_date, file_url | patient_id, doc_number | Scanned ID documents stored in MinIO |
| patient_allergies | id, patient_id (FK), allergen, type, severity, reaction, verified_by, verified_at | patient_id, allergen | Drug/food/environmental allergies |
| visits | id, patient_id (FK), visit_type, department_code, doctor_id, status, token_number, started_at, ended_at | patient_id, visit_type+status, doctor_id, started_at | All visit types; doctor_id references hr_db via event sync |
| consents | id, patient_id (FK), visit_id (FK), consent_type, version, status, signed_at, witness_name, document_url | patient_id, consent_type | Treatment, data sharing, research consents |
| next_of_kin | id, patient_id (FK), name, relationship, phone, address, is_guardian | patient_id | Required for minors |

## 4.3 appointment_db Schema

| Table | Key Columns | Indexes |
| --- | --- | --- |
| doctor_schedules | id, doctor_id, day_of_week, start_time, end_time, slot_duration_min, max_patients, location_code, is_active | doctor_id+day_of_week, is_active |
| schedule_overrides | id, doctor_id, override_date, type (holiday/extra/modified), modified_slots (JSONB) | doctor_id+override_date |
| appointments | id, patient_uhid, doctor_id, appointment_date, slot_time, type, status, source, cancellation_reason, booked_by | patient_uhid, doctor_id+appointment_date, status |
| tokens | id, appointment_id (FK), department_code, token_number, counter, status, called_at, seen_at, completed_at | department_code+status, token_number |
| waiting_queues | id, department_code, date, current_token, avg_wait_minutes, display_config (JSONB) | department_code+date |

## 4.4 opd_db Schema

| Table | Key Columns | Indexes |
| --- | --- | --- |
| opd_visits | id, visit_id (ext), patient_uhid, doctor_id, department, chief_complaint, vitals_snapshot (JSONB), status | visit_id, patient_uhid, doctor_id |
| clinical_notes | id, opd_visit_id (FK), note_type (SOAP/free), subjective, objective, assessment, plan, created_by | opd_visit_id, created_by |
| diagnoses | id, opd_visit_id (FK), icd_code, description, type (primary/secondary/differential), certainty | opd_visit_id, icd_code |
| prescriptions | id, opd_visit_id (FK), doctor_id, status, pharmacy_status, notes | opd_visit_id, pharmacy_status |
| prescription_items | id, prescription_id (FK), drug_code, drug_name, dose, frequency, route, duration_days, quantity, instructions, substitution_allowed | prescription_id, drug_code |
| investigation_orders | id, opd_visit_id (FK), test_code, test_name, urgency, clinical_info, status, result_reference | opd_visit_id, status, test_code |
| referrals | id, opd_visit_id (FK), from_doctor, to_doctor_or_dept, reason, urgency, clinical_summary, status | opd_visit_id, status |

## 4.5 billing_db Schema

| Table | Key Columns | Indexes |
| --- | --- | --- |
| charge_master | id, service_code (UNIQUE), name, cpt_code, department, base_rate, tax_percent, is_active, effective_from | service_code, department, cpt_code |
| tariffs | id, name, type (cash/insurance/corporate), is_default, effective_from, status | type, status |
| tariff_rates | id, tariff_id (FK), service_code, rate, discount_percent | tariff_id+service_code |
| invoices | id, invoice_number (UNIQUE), patient_uhid, visit_id, admission_id, type (OPD/IPD), subtotal, tax, discount, net_amount, paid_amount, balance, status | invoice_number, patient_uhid, visit_id, status |
| invoice_line_items | id, invoice_id (FK), service_code, description, quantity, unit_rate, amount, tax, discount, department, doctor_id, source_module | invoice_id |
| payments | id, invoice_id (FK), amount, payment_mode, reference_number, gateway_txn_id, collected_by, collected_at, status | invoice_id, reference_number |
| advances | id, patient_uhid, admission_id, amount, payment_mode, reference_number, status, adjusted_against_invoice_id | patient_uhid, admission_id, status |
| refunds | id, invoice_id (FK), payment_id (FK), amount, reason, approved_by, processed_at, refund_mode, status | invoice_id, status |

## 4.6 ipd_db Schema

| Table | Key Columns | Indexes |
| --- | --- | --- |
| admissions | id, admission_number (UNIQUE), patient_uhid, visit_id, type, admitting_doctor, primary_consultant, bed_id, status, admitted_at, discharged_at, estimated_cost | admission_number, patient_uhid, status, bed_id |
| beds | id, ward_id (FK), floor, room_number, bed_number, category, status, features (JSONB) | ward_id, status, category |
| wards | id, name, floor, department_code, total_beds, nurse_station_location | department_code |
| bed_transfers | id, admission_id (FK), from_bed_id, to_bed_id, reason, transferred_at, authorized_by | admission_id |
| round_notes | id, admission_id (FK), doctor_id, note_type, assessment, plan, orders (JSONB), recorded_at | admission_id, recorded_at |
| discharge_summaries | id, admission_id (FK), diagnosis_codes (JSONB), procedures (JSONB), summary_text, discharge_meds (JSONB), instructions, follow_up_date, prepared_by | admission_id |

## 4.7 lab_db Schema

| Table | Key Columns | Indexes |
| --- | --- | --- |
| test_master | id, test_code (UNIQUE), name, loinc_code, section, sample_type, container, volume_ml, tat_hours, is_active | test_code, loinc_code, section |
| test_parameters | id, test_id (FK), name, unit, data_type, display_order, reference_ranges (JSONB), critical_values (JSONB) | test_id |
| test_panels | id, panel_code, name, test_ids (JSONB), price | panel_code |
| lab_orders | id, order_number (UNIQUE), visit_id, patient_uhid, ordered_by, urgency, clinical_info, status, ordered_at | order_number, patient_uhid, status |
| lab_order_items | id, lab_order_id (FK), test_code, test_name, status, sample_id (FK) | lab_order_id, status |
| samples | id, barcode (UNIQUE), lab_order_id (FK), sample_type, collected_by, collected_at, received_at, status, rejection_reason | barcode, lab_order_id, status |
| lab_results | id, lab_order_item_id (FK), parameter_values (JSONB), tech_validated_by, tech_validated_at, doctor_validated_by, doctor_validated_at, status, report_url | lab_order_item_id, status |
| critical_alerts | id, lab_result_id (FK), parameter_name, value, notified_to (JSONB), acknowledged_by, acknowledged_at | lab_result_id |
| quality_controls | id, instrument_code, test_code, qc_level, expected_range (JSONB), observed_value, status, action_taken, performed_by, performed_at | instrument_code, test_code, performed_at |

## 4.8 Additional Database Schemas (Summary)

The following services follow the same patterns. Key tables are listed:

| Database | Key Tables |
| --- | --- |
| pharmacy_db | drug_master, drug_interactions, pharmacy_locations, pharmacy_stock, dispensings, dispensing_items, narcotic_register, drug_returns |
| radiology_db | exam_master, radiology_orders, radiology_reports, dicom_study_references, contrast_administrations, radiation_dose_log |
| nursing_db | nursing_assessments, vital_signs, intake_outputs, medication_administrations, care_plans, care_plan_interventions, shift_handovers, nurse_assignments |
| emergency_db | er_encounters, triage_assessments, trauma_activations, resuscitation_logs, mlc_registrations, er_dispositions |
| ot_db | ot_rooms, surgery_requests, surgery_schedules, surgical_teams, anesthesia_records, surgical_safety_checklists, surgical_notes, specimen_tracking |
| inventory_db | item_master, vendors, rate_contracts, purchase_indents, purchase_orders, grn_entries, grn_items, stock_entries, stock_transfers, stock_adjustments |
| hr_db | employees, departments, designations, attendance_records, leave_types, leave_balances, leave_requests, salary_structures, salary_components, payroll_runs, payslips |
| bloodbank_db | donors, donor_screenings, blood_bags, blood_components, tti_results, cross_match_requests, blood_issues, transfusion_reactions |
| dietary_db | diet_types, diet_orders, meal_schedules, meal_preparations, meal_deliveries, nutrition_plans |
| insurance_db | insurance_companies, tpa_master, patient_policies, pre_auth_requests, claims, claim_items, settlements, rejections |
| quality_db | quality_indicators, indicator_values, incident_reports, capa_actions, infection_surveillance, audit_schedules, audit_findings, document_controls |
| analytics_db | fact_patient_visits, fact_revenue, fact_lab_orders, dim_time, dim_department, dim_doctor, dim_diagnosis (Star schema) |

# 5. Phase 1: Foundation (Weeks 1-16)

## 5.1 Phase 1 Overview

Phase 1 establishes the foundational infrastructure, shared libraries, and core business modules that all subsequent phases depend on. At the end of this phase, the hospital can register patients, book appointments, conduct OPD consultations, write prescriptions, and generate basic billing.

| Attribute | Detail |
| --- | --- |
| Duration | 16 weeks (4 months) |
| Services Delivered | hm-gateway, hm-auth-service, hm-config-server, hm-discovery-server, hm-patient-service, hm-appointment-service, hm-opd-service, hm-billing-service, hm-master-data-service, hm-notification-service |
| Team Size | 8-10 developers, 1 architect, 1 DevOps, 2 QA, 1 BA, 1 PM |
| Key Milestone | OPD go-live: patients can register, consult, receive prescriptions, and pay bills |

## 5.2 Sprint Breakdown - Phase 1

### Sprint 1-2 (Weeks 1-4): Infrastructure & Shared Libraries

| Task | Owner | Deliverable |
| --- | --- | --- |
| Set up Git repositories, branching strategy (GitFlow) | DevOps | All repos created with branch protection rules |
| Create hm-bom parent POM with dependency management | Architect | Parent POM published to Nexus/Artifactory |
| Build hm-common library (base DTOs, exceptions, pagination, audit) | Backend Lead | Library v1.0 published |
| Build hm-security library (JWT filter, RBAC annotations, Keycloak) | Security Dev | Library v1.0 published |
| Build hm-kafka-common (event DTOs, producer/consumer config, DLQ) | Backend Dev | Library v1.0 published |
| Build hm-audit library (audit aspect, trail entity, Kafka publisher) | Backend Dev | Library v1.0 published |
| Set up Keycloak with hospital realm, roles, clients | DevOps/Security | Keycloak configured with all Phase 1 roles |
| Deploy PostgreSQL instances for Phase 1 services (via Docker) | DevOps | 6 PostgreSQL databases running |
| Deploy Kafka cluster (3-broker), Redis, Elasticsearch | DevOps | Infrastructure stack running |
| Set up hm-config-server with Git-backed config | Backend Dev | Config server serving all service configs |
| Set up hm-discovery-server (Consul/Eureka) | Backend Dev | Service discovery operational |
| Set up hm-gateway with routing, rate limiting, CORS | Backend Dev | Gateway routing to all Phase 1 services |
| Set up CI/CD pipeline (build, test, Docker build, deploy to dev) | DevOps | Pipeline green for all repos |
| Set up monitoring stack (Prometheus + Grafana + ELK + Jaeger) | DevOps | Dashboards visible for all services |
| Create Docker Compose for local development | DevOps | docker-compose up starts full stack locally |
| Set up Kubernetes namespace, Helm chart templates | DevOps | K8s dev namespace with Helm base charts |

### Sprint 3-4 (Weeks 5-8): Patient Registration & Master Data

| Task | Owner | Deliverable |
| --- | --- | --- |
| hm-master-data-service: ICD-10 code import and search API | Backend Dev 1 | ICD-10 codes loaded, searchable via Elasticsearch |
| hm-master-data-service: Drug master import (generic, brand, interactions) | Backend Dev 1 | Drug database with interaction checking API |
| hm-master-data-service: Department, service catalog, doctor master | Backend Dev 1 | All reference data APIs operational |
| hm-patient-service: Patient CRUD with UHID generation | Backend Dev 2 | Patient registration with auto UHID |
| hm-patient-service: Patient search (fuzzy name, phone, ID) | Backend Dev 2 | Trigram + full-text search working |
| hm-patient-service: Contact, address, document, allergy management | Backend Dev 2 | All sub-entity APIs complete |
| hm-patient-service: Duplicate detection and merge | Backend Dev 3 | Duplicate flagging and admin merge API |
| hm-patient-service: Visit creation and management | Backend Dev 3 | Visit lifecycle APIs |
| hm-patient-service: Consent capture API | Backend Dev 3 | Consent recording with document upload |
| hm-patient-service: Kafka events (patient.registered, patient.updated) | Backend Dev 2 | Events published on patient changes |
| hm-notification-service: SMS, email, push notification engine | Backend Dev 4 | Notification templates + delivery APIs |
| hm-notification-service: WhatsApp Business API integration | Backend Dev 4 | WhatsApp message delivery |
| Integration testing: patient registration end-to-end | QA | E2E test suite passing |
| Flyway migrations for patient_db, master_db, notification_db | Backend Devs | All migration scripts versioned and tested |

### Sprint 5-6 (Weeks 9-12): Appointments & OPD

| Task | Owner | Deliverable |
| --- | --- | --- |
| hm-appointment-service: Doctor schedule CRUD | Backend Dev 3 | Weekly templates + override APIs |
| hm-appointment-service: Slot availability engine | Backend Dev 3 | Real-time available slot calculation |
| hm-appointment-service: Appointment booking, cancel, reschedule | Backend Dev 3 | Appointment lifecycle APIs |
| hm-appointment-service: Token generation and queue management | Backend Dev 3 | Token + queue APIs with wait-time estimation |
| hm-appointment-service: Appointment reminder events via Kafka | Backend Dev 3 | Reminder events consumed by notification-service |
| hm-opd-service: OPD visit creation and doctor workstation API | Backend Dev 5 | Doctor queue + visit data APIs |
| hm-opd-service: Clinical notes (SOAP) CRUD | Backend Dev 5 | Clinical documentation APIs |
| hm-opd-service: Diagnosis entry with ICD-10 integration | Backend Dev 5 | Diagnosis CRUD with code lookup |
| hm-opd-service: Prescription writing with drug interaction check | Backend Dev 6 | Prescription API with safety checks via master-data-service |
| hm-opd-service: Investigation ordering (lab + radiology placeholders) | Backend Dev 6 | Order creation APIs with Kafka events |
| hm-opd-service: Referral management | Backend Dev 6 | Referral CRUD and notification |
| hm-opd-service: Follow-up scheduling integration | Backend Dev 5 | Auto-appointment creation for follow-ups |
| Integration testing: appointment + OPD workflows | QA | E2E OPD consultation flow tested |

### Sprint 7-8 (Weeks 13-16): Billing & Go-Live Prep

| Task | Owner | Deliverable |
| --- | --- | --- |
| hm-billing-service: Charge master and tariff management APIs | Backend Dev 7 | Charge master CRUD with multi-tariff support |
| hm-billing-service: Auto charge capture from OPD events | Backend Dev 7 | Kafka consumer for opd.consultation.completed events |
| hm-billing-service: Invoice generation (OPD) | Backend Dev 7 | OPD invoice generation with line items |
| hm-billing-service: Payment collection (cash, card, UPI) | Backend Dev 8 | Payment API with gateway integration |
| hm-billing-service: Receipt printing API | Backend Dev 8 | Configurable receipt templates |
| hm-billing-service: Advance collection and adjustment | Backend Dev 8 | Advance deposit management |
| hm-billing-service: Discount management with approval workflow | Backend Dev 7 | Discount request/approve APIs |
| hm-billing-service: Refund processing | Backend Dev 8 | Refund CRUD with authorization |
| Security hardening: penetration testing, OWASP review | Security Dev | Security report with all critical issues resolved |
| Performance testing: load test all Phase 1 APIs | QA/DevOps | Performance report, SLA thresholds met |
| User acceptance testing (UAT) | BA + QA | UAT sign-off from hospital stakeholders |
| Data migration: existing patient data import | Backend Lead | Migration scripts tested and validated |
| Staff training: front desk, doctors, billing | BA/PM | Training completed for 50+ users |
| Go-live preparation: production deployment, monitoring, support | DevOps/Team | Phase 1 LIVE in production |

# 6. Phase 2: Clinical Core (Weeks 17-32)

## 6.1 Phase 2 Overview

| Attribute | Detail |
| --- | --- |
| Duration | 16 weeks (4 months) |
| Services Delivered | hm-ipd-service, hm-emergency-service, hm-lab-service, hm-radiology-service, hm-pharmacy-service, hm-nursing-service, hm-ot-service |
| Dependencies | Phase 1 services stable and live |
| Team Growth | +4 developers (12-14 total), +1 QA, +1 clinical BA |
| Key Milestone | Full clinical operations: IPD admissions, lab/radiology results, pharmacy dispensing, nursing documentation |

## 6.2 Sprint Breakdown - Phase 2

### Sprint 9-10 (Weeks 17-20): IPD & Emergency

| Task | Owner | Deliverable |
| --- | --- | --- |
| hm-ipd-service: Ward and bed master setup APIs | Backend Dev A | Ward/bed hierarchy with JSONB features |
| hm-ipd-service: Bed availability board API (real-time via WebSocket) | Backend Dev A | Live bed status dashboard data |
| hm-ipd-service: Admission workflow (planned, emergency, transfer) | Backend Dev A | Admission creation with bed assignment |
| hm-ipd-service: Bed transfer with auto billing rate update | Backend Dev B | Transfer API with Kafka billing event |
| hm-ipd-service: Round notes and progress notes CRUD | Backend Dev B | Clinical documentation for inpatients |
| hm-ipd-service: Discharge workflow (summary, billing, meds, follow-up) | Backend Dev B | Full discharge APIs with event publishing |
| hm-emergency-service: Rapid registration (minimal dataset) | Backend Dev C | Quick ER registration linked to patient-service |
| hm-emergency-service: ESI triage assessment | Backend Dev C | Triage scoring with priority classification |
| hm-emergency-service: ER tracking board API (WebSocket) | Backend Dev C | Real-time patient tracking with color coding |
| hm-emergency-service: MLC registration and police notification | Backend Dev C | MLC workflow with audit trail |
| hm-emergency-service: Disposition and ER-to-IPD handoff | Backend Dev C | Seamless transition to admission |
| Update hm-billing-service: IPD per-day charges, ER charges | Backend Dev 7 | Billing Kafka consumers for IPD/ER events |

### Sprint 11-12 (Weeks 21-24): Lab & Radiology

| Task | Owner | Deliverable |
| --- | --- | --- |
| hm-lab-service: Test catalog with LOINC, reference ranges, critical values | Backend Dev D | Test master APIs with parameter management |
| hm-lab-service: Lab order processing from OPD/IPD events | Backend Dev D | Kafka consumer for investigation orders |
| hm-lab-service: Sample collection with barcode generation | Backend Dev D | Sample lifecycle APIs with barcode |
| hm-lab-service: Result entry (manual + instrument interface prep) | Backend Dev E | Result CRUD with delta checking |
| hm-lab-service: Technical and medical validation workflow | Backend Dev E | Two-step validation with role-based access |
| hm-lab-service: Critical value alerting via Kafka | Backend Dev D | Critical alert events consumed by notification-service |
| hm-lab-service: Report generation and PDF rendering | Backend Dev E | Lab report template engine |
| hm-lab-service: QC module for instrument quality tracking | Backend Dev E | Levey-Jennings chart data APIs |
| hm-radiology-service: Exam master and modality configuration | Backend Dev F | Radiology catalog APIs |
| hm-radiology-service: Imaging order management | Backend Dev F | Order lifecycle with scheduling |
| hm-radiology-service: DICOM MWL integration (HL7/DICOM) | Backend Dev F | Modality worklist push to equipment |
| hm-radiology-service: Reporting (structured + narrative) | Backend Dev F | Report creation and verification workflow |
| hm-radiology-service: PACS integration (WADO-RS) | Backend Dev F | Image retrieval API via DICOMweb |
| Update billing: lab and radiology charge capture | Backend Dev 7 | Auto-billing from lab/radiology events |

### Sprint 13-14 (Weeks 25-28): Pharmacy & Nursing

| Task | Owner | Deliverable |
| --- | --- | --- |
| hm-pharmacy-service: Drug master sync from master-data-service | Backend Dev G | Drug catalog with formulary flags |
| hm-pharmacy-service: OPD dispensing against prescriptions | Backend Dev G | Prescription queue + dispensing APIs |
| hm-pharmacy-service: IPD dispensing (unit dose, ward stock) | Backend Dev G | Inpatient medication dispensing |
| hm-pharmacy-service: Batch/expiry tracking and stock management | Backend Dev G | Real-time stock with FEFO issuing |
| hm-pharmacy-service: Narcotic register with double verification | Backend Dev G | Controlled substance workflow |
| hm-pharmacy-service: Return and substitution management | Backend Dev G | Return/substitute APIs with approvals |
| hm-nursing-service: Initial assessment and care plan CRUD | Backend Dev H | Nursing assessment APIs |
| hm-nursing-service: Vital signs recording (configurable frequency) | Backend Dev H | Vitals API with trending data |
| hm-nursing-service: MAR (Medication Administration Record) | Backend Dev H | MAR grid with barcode verification |
| hm-nursing-service: I/O charting | Backend Dev H | Intake-output recording APIs |
| hm-nursing-service: Pain, fall risk, pressure ulcer assessments | Backend Dev H | Standardized assessment tool APIs |
| hm-nursing-service: Shift handover (SBAR format) | Backend Dev H | Structured handoff APIs |
| Update billing: pharmacy charge capture | Backend Dev 8 | Auto-billing from dispensing events |

### Sprint 15-16 (Weeks 29-32): OT, Integration & Phase 2 Go-Live

| Task | Owner | Deliverable |
| --- | --- | --- |
| hm-ot-service: OT room master and availability calendar | Backend Dev I | OT scheduling engine |
| hm-ot-service: Surgery request and approval workflow | Backend Dev I | Surgery request APIs with multi-level approval |
| hm-ot-service: WHO Surgical Safety Checklist APIs | Backend Dev I | Three-phase checklist (Sign-in, Time-out, Sign-out) |
| hm-ot-service: Anesthesia record and surgical notes | Backend Dev I | Intra-operative documentation |
| hm-ot-service: Specimen tracking to lab | Backend Dev I | Specimen handoff with lab-service integration |
| hm-ot-service: OT utilization analytics | Backend Dev I | Metrics: on-time start, turnaround, cancellations |
| Lab instrument interfacing (ASTM/LIS2-A2) | Integration Dev | Bi-directional instrument communication |
| DICOM worklist testing with real modalities | Integration Dev | MWL verified with CT/MRI/X-ray |
| Cross-service integration testing: full IPD journey | QA Team | Admit-to-discharge E2E test suite |
| Performance testing for Phase 2 services | QA/DevOps | Load test results within SLA |
| UAT for IPD, ER, Lab, Radiology, Pharmacy, Nursing, OT | BA + Clinical BA | UAT sign-off from clinical staff |
| Phase 2 data migration (existing lab catalogs, drug data) | Backend Lead | Migration validated |
| Phase 2 staff training (nursing, lab, pharmacy, OT) | BA/PM | Training for 100+ clinical users |
| Phase 2 production deployment and go-live | DevOps/Team | Phase 2 LIVE |

# 7. Phase 3: Support Services (Weeks 33-44)

## 7.1 Phase 3 Overview

| Attribute | Detail |
| --- | --- |
| Duration | 12 weeks (3 months) |
| Services Delivered | hm-inventory-service, hm-hr-service, hm-bloodbank-service, hm-dietary-service |
| Dependencies | Phase 1 + 2 services stable |
| Team Size | Same team (12-14 devs), reassigned from completed Phase 2 work |
| Key Milestone | Complete supply chain, HR operations, blood bank, and dietary management |

## 7.2 Sprint Breakdown - Phase 3

### Sprint 17-18 (Weeks 33-36): Inventory & HR

| Task | Owner | Deliverable |
| --- | --- | --- |
| hm-inventory-service: Item master, vendor master, store locations | Backend Dev A+B | Master data APIs for supply chain |
| hm-inventory-service: Purchase indent, PO, approval workflow | Backend Dev A | Procurement cycle APIs |
| hm-inventory-service: GRN with quality inspection and 3-way matching | Backend Dev A | Goods receipt with validation |
| hm-inventory-service: Stock management (batch, expiry, FIFO/FEFO) | Backend Dev B | Real-time multi-store stock APIs |
| hm-inventory-service: Stock transfer between stores/departments | Backend Dev B | Inter-store transfer with approval |
| hm-inventory-service: Auto-reorder alerts and EOQ calculation | Backend Dev B | Alert engine with configurable thresholds |
| hm-inventory-service: ABC/VED analysis APIs | Backend Dev A | Inventory analytics endpoints |
| hm-hr-service: Employee master CRUD with document management | Backend Dev C+D | Employee lifecycle APIs |
| hm-hr-service: Department, designation, org hierarchy | Backend Dev C | Organization structure APIs |
| hm-hr-service: Attendance (biometric integration), shift management | Backend Dev C | Attendance recording with shift engine |
| hm-hr-service: Leave management (types, balances, requests, approvals) | Backend Dev D | Leave workflow APIs |
| hm-hr-service: Payroll engine (salary structure, computation, statutory) | Backend Dev D | Payroll processing with pay slip generation |
| hm-hr-service: Credentialing (license tracking, CME, renewals) | Backend Dev D | Credential verification APIs |

### Sprint 19-20 (Weeks 37-40): Blood Bank & Dietary

| Task | Owner | Deliverable |
| --- | --- | --- |
| hm-bloodbank-service: Donor registration and screening | Backend Dev E+F | Donor lifecycle APIs with deferral management |
| hm-bloodbank-service: Blood collection with bag barcode tracking | Backend Dev E | Collection workflow with barcode generation |
| hm-bloodbank-service: Blood grouping, typing, TTI testing | Backend Dev E | Testing workflow with result recording |
| hm-bloodbank-service: Component preparation and inventory | Backend Dev F | Component separation with expiry tracking |
| hm-bloodbank-service: Cross-match and blood issue workflow | Backend Dev F | Compatibility testing and issue APIs |
| hm-bloodbank-service: Transfusion reaction reporting | Backend Dev F | Reaction recording and investigation workflow |
| hm-bloodbank-service: FIFO issue, wastage tracking, blood camp | Backend Dev E | Optimization and camp management APIs |
| hm-dietary-service: Diet type master and diet order integration | Backend Dev G | Diet catalog with IPD integration |
| hm-dietary-service: Meal scheduling and kitchen prep lists | Backend Dev G | Meal generation engine per ward |
| hm-dietary-service: Meal delivery tracking | Backend Dev G | Delivery status APIs |
| hm-dietary-service: Nutrition planning and calorie tracking | Backend Dev G | Dietician assessment APIs |
| Pharmacy-Inventory integration: auto PO from pharmacy reorder | Integration Dev | Cross-service reorder workflow |
| Billing integration: blood bank charges, implant billing from inventory | Backend Dev 7 | New charge capture consumers |

### Sprint 21-22 (Weeks 41-44): Integration, Testing & Phase 3 Go-Live

| Task | Owner | Deliverable |
| --- | --- | --- |
| Cross-module integration: inventory consumption from pharmacy, OT, lab | Integration Dev | Automatic stock deduction workflows |
| HR integration: doctor schedules sync, employee reference in all modules | Backend Dev C | Employee lookup available across services |
| Blood bank integration: cross-match from IPD/OT, billing auto-capture | Backend Dev F | End-to-end blood request flow |
| Performance testing: Phase 3 services | QA/DevOps | Load test results within SLA |
| UAT: inventory, HR, blood bank, dietary workflows | BA + Clinical BA | UAT sign-off from admin and clinical staff |
| Data migration: vendor data, employee data, blood bank historical data | Backend Lead | Migration validated |
| Staff training: store managers, HR, blood bank officers, dieticians | BA/PM | Training completed for relevant staff |
| Phase 3 production deployment and go-live | DevOps/Team | Phase 3 LIVE |

# 8. Phase 4: Advanced Capabilities (Weeks 45-56)

## 8.1 Phase 4 Overview

| Attribute | Detail |
| --- | --- |
| Duration | 12 weeks (3 months) |
| Services Delivered | hm-insurance-service, hm-quality-service, hm-analytics-service, hm-patient-portal, hm-fhir-service |
| Dependencies | Phase 1-3 services stable |
| Team Size | Same team with focus shift to analytics and interoperability |
| Key Milestone | Insurance processing, quality management, executive dashboards, patient portal, FHIR interoperability |

## 8.2 Sprint Breakdown - Phase 4

### Sprint 23-24 (Weeks 45-48): Insurance & Quality

| Task | Owner | Deliverable |
| --- | --- | --- |
| hm-insurance-service: Insurance/TPA company master | Backend Dev A | Insurance master APIs |
| hm-insurance-service: Patient policy registration and verification | Backend Dev A | Policy management APIs |
| hm-insurance-service: Pre-authorization workflow | Backend Dev A | Pre-auth request/approve/reject APIs |
| hm-insurance-service: Claim generation from billing data | Backend Dev B | Auto claim creation from IPD invoices |
| hm-insurance-service: Claim submission tracking and follow-up | Backend Dev B | Claim lifecycle with status tracking |
| hm-insurance-service: Settlement reconciliation | Backend Dev B | Settlement matching with billing |
| hm-quality-service: Quality indicator definitions and data collection | Backend Dev C | Automated indicator collection from clinical events |
| hm-quality-service: Incident reporting and investigation workflow | Backend Dev C | Anonymous/identified reporting with RCA |
| hm-quality-service: CAPA tracking | Backend Dev C | Corrective action lifecycle APIs |
| hm-quality-service: Infection surveillance and antibiogram | Backend Dev D | HAI tracking with antibiogram generation |
| hm-quality-service: Document control and audit management | Backend Dev D | Policy/SOP versioning with audit scheduling |
| hm-quality-service: NABH/JCI standard mapping and compliance score | Backend Dev D | Accreditation readiness dashboard data |

### Sprint 25-26 (Weeks 49-52): Analytics & Patient Portal

| Task | Owner | Deliverable |
| --- | --- | --- |
| hm-analytics-service: Star schema design and ETL pipeline from Kafka | Backend Dev E | Data warehouse with Kafka consumers |
| hm-analytics-service: Clinical reports (patient stats, diagnosis, procedures) | Backend Dev E | Clinical analytics APIs |
| hm-analytics-service: Financial reports (revenue, receivables, collections) | Backend Dev F | Financial dashboard data |
| hm-analytics-service: Operational reports (bed occupancy, TAT, utilization) | Backend Dev F | Operational metrics APIs |
| hm-analytics-service: Executive KPI dashboard API | Backend Dev E | CEO/CMO dashboard data endpoints |
| hm-analytics-service: Ad-hoc report builder API | Backend Dev F | Dynamic query builder for power users |
| hm-analytics-service: Scheduled report generation and email delivery | Backend Dev E | Cron-based report dispatch |
| hm-patient-portal: Patient login (OTP/password) and profile | Backend Dev G | Patient self-service auth |
| hm-patient-portal: Appointment booking and management | Backend Dev G | Online booking via appointment-service |
| hm-patient-portal: Lab/radiology report download | Backend Dev G | Report access with consent verification |
| hm-patient-portal: Bill view and online payment | Backend Dev H | Payment gateway integration for patients |
| hm-patient-portal: Feedback submission | Backend Dev H | Feedback collection and routing |
| hm-patient-portal: Teleconsultation booking | Backend Dev H | Video call scheduling with doctor calendar |

### Sprint 27-28 (Weeks 53-56): FHIR, Final Integration & Project Closure

| Task | Owner | Deliverable |
| --- | --- | --- |
| hm-fhir-service: HAPI FHIR server setup with custom resource providers | Backend Dev I | FHIR R4 server with Patient, Encounter, Observation resources |
| hm-fhir-service: Patient FHIR resource mapping from patient-service | Backend Dev I | FHIR Patient search and read |
| hm-fhir-service: Encounter, Condition, MedicationRequest mapping | Backend Dev I | Clinical FHIR resources from OPD/IPD |
| hm-fhir-service: DiagnosticReport, Observation from lab/radiology | Backend Dev I | Lab/radiology FHIR resources |
| hm-fhir-service: ABDM integration (India) / national health ID linking | Backend Dev I | National health ecosystem connectivity |
| End-to-end regression testing: all 26 services | QA Team | Full regression suite passing |
| Security audit: comprehensive penetration test | Security Dev | Security audit report, all critical issues resolved |
| Performance testing: full system under peak load | QA/DevOps | System handles 2000+ concurrent users |
| Disaster recovery drill | DevOps | DR test successful, RTO/RPO within target |
| Final UAT for Phase 4 features | BA + Stakeholders | UAT sign-off |
| Operations runbook and handover documentation | DevOps/Architect | Complete ops guide |
| Phase 4 production deployment and system-wide go-live | DevOps/Team | FULL SYSTEM LIVE |
| 30-day hypercare support | Full Team | Issue resolution within SLA |
| Project closure and handover to operations | PM | Signed project closure report |

# 9. CI/CD Pipeline Design

## 9.1 Pipeline Stages

Every microservice follows the same pipeline stages, triggered on each Git push:

| Stage | Tools | Actions | Failure Action |
| --- | --- | --- | --- |
| 1. Code Quality | SonarQube, Checkstyle, SpotBugs | Static analysis, code coverage check (min 80%), bug detection | Block merge, notify developer |
| 2. Unit Tests | JUnit 5, Mockito | Run all unit tests | Block merge |
| 3. Integration Tests | Testcontainers (PostgreSQL, Kafka, Redis) | Run integration tests with real containers | Block merge |
| 4. Build | Maven, Docker | mvn package, docker build, push to registry | Notify team |
| 5. Security Scan | Trivy, OWASP Dependency Check | Container image scan, dependency vulnerability scan | Block deploy if critical CVE |
| 6. Deploy to Dev | Helm, Kubernetes | Deploy to dev namespace | Notify DevOps |
| 7. Smoke Tests | REST Assured, Postman/Newman | Health check, basic API contract tests | Rollback deploy |
| 8. Deploy to Staging | Helm, Kubernetes (manual approval) | Deploy to staging after dev validation | Block further promotion |
| 9. E2E Tests | Cypress / Playwright (UI), REST Assured (API) | Full end-to-end workflow tests | Block production deploy |
| 10. Deploy to Production | Helm, ArgoCD (manual approval) | Rolling update deployment | Auto-rollback on health check failure |

## 9.2 Branching Strategy

| Branch | Purpose | Deploys To |
| --- | --- | --- |
| main | Production-ready code | Production (via tag/release) |
| develop | Integration branch for features | Dev environment (auto) |
| feature/* | Individual feature branches | Dev (on merge to develop) |
| release/* | Release candidates | Staging (auto), Production (manual) |
| hotfix/* | Emergency production fixes | Production (fast-track) |

## 9.3 Docker Image Strategy

- Base image: eclipse-temurin:21-jre-alpine (minimal JRE)

- Multi-stage Dockerfile: build stage (Maven) + runtime stage (JRE only)

- Image tagging: {service}:{version}-{git-sha} for traceability

- Image registry: Harbor / AWS ECR / GCP Artifact Registry

- Image scanning on every push with Trivy

# 10. Infrastructure and Kubernetes Deployment

## 10.1 Kubernetes Cluster Design

| Component | Specification |
| --- | --- |
| Cluster Type | Managed Kubernetes (EKS / AKS / GKE) or on-premise K8s via kubeadm/RKE2 |
| Namespaces | hm-dev, hm-staging, hm-production, hm-monitoring, hm-infra |
| Node Pools | app-pool (application services), db-pool (stateful workloads), monitoring-pool |
| Ingress Controller | NGINX Ingress with TLS termination (cert-manager for Let's Encrypt) |
| Service Mesh | Istio (optional, for mTLS, traffic management, observability) |
| Storage | CSI driver for persistent volumes (PostgreSQL, Kafka, Elasticsearch, Redis) |
| Secrets Management | Kubernetes Secrets + HashiCorp Vault for sensitive credentials |
| Auto-scaling | HPA (Horizontal Pod Autoscaler) based on CPU/memory + custom Kafka lag metrics |

## 10.2 Resource Allocation Per Service

| Service Category | CPU Request | CPU Limit | Memory Request | Memory Limit | Replicas (Prod) |
| --- | --- | --- | --- | --- | --- |
| Infrastructure (gateway, config, discovery) | 250m | 500m | 512Mi | 1Gi | 2-3 |
| High-traffic (patient, OPD, billing, appointment) | 500m | 1000m | 1Gi | 2Gi | 3-5 |
| Medium-traffic (IPD, lab, pharmacy, nursing) | 500m | 1000m | 1Gi | 2Gi | 2-3 |
| Low-traffic (dietary, quality, blood bank) | 250m | 500m | 512Mi | 1Gi | 2 |
| Stateful (PostgreSQL per service) | 1000m | 2000m | 2Gi | 4Gi | Primary + 1 replica |
| Infrastructure (Kafka, Redis, Elasticsearch) | 1000m | 2000m | 2Gi | 8Gi | 3 (cluster) |

## 10.3 Production Architecture Summary

Production environment topology:

- Load Balancer (cloud LB or HAProxy) with SSL termination

- NGINX Ingress Controller routing to API Gateway (hm-gateway, 3 replicas)

- API Gateway routes to internal services via Kubernetes service discovery

- Each microservice: 2-5 replicas with HPA, liveness/readiness probes

- PostgreSQL: Primary + streaming replica per service database, pgBouncer for connection pooling

- Kafka: 3-broker cluster with replication factor 3, min ISR 2

- Redis: 3-node Sentinel cluster for caching and session management

- Elasticsearch: 3-node cluster (2 data + 1 master) for search

- MinIO: Distributed mode (4+ nodes) for object storage

- Monitoring: Prometheus (2 replicas) + Grafana + AlertManager + PagerDuty integration

- Logging: Fluentd DaemonSet collecting from all pods into Elasticsearch + Kibana

- Tracing: Jaeger with Elasticsearch backend for distributed trace storage

## 10.4 Docker Compose for Local Development

A docker-compose.yml in the hm-infra repository allows developers to spin up the entire infrastructure locally:

- PostgreSQL (single instance with multiple databases)

- Kafka (single broker) + Zookeeper

- Redis (single instance)

- Elasticsearch (single node)

- Keycloak (with pre-configured realm)

- MinIO (single instance)

- Mailhog (email testing)

Individual services are run from IDE or via mvn spring-boot:run, connecting to Dockerized infrastructure.

# 11. Team Structure and Responsibilities

## 11.1 Core Team Composition

| Role | Count | Responsibilities |
| --- | --- | --- |
| Technical Architect | 1 | Architecture decisions, code reviews, cross-service design, ADRs |
| Backend Lead | 1 | Shared libraries, code quality standards, mentoring, complex integrations |
| Senior Backend Developers | 4-6 | Microservice development, API design, Kafka integration |
| Mid-Level Backend Developers | 4-6 | Feature implementation, unit/integration tests, bug fixes |
| DevOps Engineer | 1-2 | CI/CD, Kubernetes, infrastructure, monitoring, security |
| Security Engineer | 1 | Keycloak setup, penetration testing, security reviews, HIPAA compliance |
| QA Engineers | 2-3 | Test automation, E2E testing, performance testing, UAT coordination |
| Business Analyst (Clinical) | 1-2 | Clinical workflow validation, stakeholder communication, UAT facilitation |
| Project Manager | 1 | Sprint planning, risk management, stakeholder reporting, go-live coordination |
| UI/UX Designer | 1 | Screen designs, component library, user research |
| Frontend Developers | 2-3 | React/Angular SPA, responsive design, component development |

## 11.2 Team Scaling by Phase

| Phase | Backend | Frontend | QA | DevOps | BA/PM | Total |
| --- | --- | --- | --- | --- | --- | --- |
| Phase 1 (Foundation) | 8 | 2 | 2 | 2 | 2 | 16 |
| Phase 2 (Clinical Core) | 12 | 3 | 3 | 2 | 3 | 23 |
| Phase 3 (Support Services) | 10 | 3 | 2 | 1 | 2 | 18 |
| Phase 4 (Advanced) | 10 | 3 | 3 | 2 | 2 | 20 |

# 12. Testing Strategy

## 12.1 Testing Pyramid

| Level | Scope | Tools | Coverage Target | Run Frequency |
| --- | --- | --- | --- | --- |
| Unit Tests | Individual classes, methods, business logic | JUnit 5, Mockito, AssertJ | 80%+ line coverage | Every commit |
| Integration Tests | Service + database + Kafka + Redis | Testcontainers, Spring Boot Test | All repository and Kafka flows | Every commit |
| Contract Tests | API compatibility between services | Spring Cloud Contract / Pact | All inter-service APIs | Every PR |
| E2E Tests (API) | Full workflow across multiple services | REST Assured, Karate | Critical patient journeys | Nightly + pre-release |
| E2E Tests (UI) | Frontend workflows | Cypress / Playwright | Core user flows | Nightly |
| Performance Tests | Load, stress, endurance | Gatling / k6 | SLA thresholds | Weekly + pre-release |
| Security Tests | OWASP Top 10, dependency scan | OWASP ZAP, Trivy, Snyk | Zero critical/high vulns | Every build + quarterly pentest |
| Chaos Tests | Resilience under failure | Chaos Monkey / Litmus | Service recovery within SLA | Monthly |

## 12.2 Key Test Scenarios

The following critical clinical workflows must have comprehensive E2E test coverage:

- Complete OPD journey: register patient, book appointment, consult, prescribe, order labs, bill, pay

- Full IPD journey: admit, assign bed, nursing assessment, doctor rounds, lab/radiology orders, results, surgery, pharmacy, discharge, final bill

- Emergency flow: rapid registration, triage, treatment, disposition (admit/discharge/transfer)

- Lab lifecycle: order received, sample collected, results entered, validated, critical alert, report generated

- Pharmacy: prescription received, drug interaction check, dispense with barcode, narcotic verification

- Blood bank: donor screen, collect, test, prepare components, cross-match, issue, transfusion reaction

- Insurance: pre-auth request, approval, IPD treatment, claim generation, submission, settlement

- Cross-service billing: charges from OPD + lab + radiology + pharmacy automatically captured in invoice

# 13. Monitoring and Observability

## 13.1 Three Pillars

| Pillar | Tool | What We Track |
| --- | --- | --- |
| Metrics | Prometheus + Grafana | JVM metrics (heap, GC, threads), API latency (p50/p95/p99), request rate, error rate, Kafka consumer lag, DB connection pool, cache hit ratio |
| Logging | ELK Stack (Fluentd + Elasticsearch + Kibana) | Structured JSON logs with correlation ID, request/response logging at gateway, error stack traces, audit events |
| Tracing | Jaeger / Zipkin via Micrometer Tracing | Distributed request traces across services, bottleneck identification, dependency maps |

## 13.2 Alerting Rules

| Alert | Condition | Severity | Notification |
| --- | --- | --- | --- |
| Service Down | Health check failing for > 30 seconds | Critical | PagerDuty + SMS + Slack |
| High Error Rate | > 5% error rate over 5 minutes | Critical | PagerDuty + Slack |
| High Latency | p95 latency > 2 seconds for 5 minutes | Warning | Slack + Email |
| Database Connection Pool Exhausted | Active connections > 90% of max | Critical | PagerDuty + Slack |
| Kafka Consumer Lag | Lag > 10000 messages for 10 minutes | Warning | Slack |
| Disk Usage | > 85% disk utilization | Warning | Slack + Email |
| Certificate Expiry | TLS cert expires within 14 days | Warning | Email + Slack |
| Failed Login Attempts | > 10 failed logins for same user in 5 minutes | Security | Security team + Slack |

## 13.3 Grafana Dashboard Catalog

- System Overview: all services health, request rates, error rates at a glance

- Per-Service Dashboard: JVM metrics, API metrics, DB metrics for each microservice

- Kafka Dashboard: topic throughput, consumer lag, partition distribution

- PostgreSQL Dashboard: query performance, connection pool, replication lag, table sizes

- Business Dashboard: patient registrations/day, appointments, lab orders, revenue (pulled from analytics-service)

- Security Dashboard: failed logins, blocked requests, certificate status

# 14. Risk Management

## 14.1 Technical Risks

| Risk | Probability | Impact | Mitigation Strategy |
| --- | --- | --- | --- |
| Microservice complexity leads to distributed debugging challenges | High | Medium | Invest in observability (Jaeger tracing, correlation IDs) from Day 1; train team on distributed debugging |
| Data consistency issues across service boundaries | High | High | Use saga pattern for transactions, event sourcing for audit-critical flows, idempotent consumers |
| Kafka message ordering and delivery guarantees | Medium | High | Partition by entity ID, use exactly-once semantics where available, dead letter queues |
| Database schema migration conflicts in CI/CD | Medium | Medium | Flyway with strict versioning, migration review as part of PR process |
| Performance degradation under peak hospital load | Medium | High | Regular load testing (weekly), HPA auto-scaling, Redis caching, database query optimization |
| Lab instrument interface compatibility issues | High | Medium | Early POC with hospital instruments, ASTM middleware, fallback to manual result entry |
| DICOM/PACS integration complexity | Medium | Medium | Use proven libraries (dcm4che), early integration testing with hospital PACS |
| Keycloak single point of failure | Low | Critical | Keycloak HA cluster (2+ nodes), database replication, session persistence in Redis |

## 14.2 Project Risks

| Risk | Probability | Impact | Mitigation Strategy |
| --- | --- | --- | --- |
| Clinical staff resistance to digital workflows | High | High | Clinical BA embedded in team, super-user program, gradual rollout, parallel run period |
| Scope creep from hospital stakeholders | High | Medium | Strict change control board, MoSCoW backlog, phase gates with sign-off |
| Key developer attrition mid-project | Medium | High | Knowledge sharing sessions, pair programming, comprehensive documentation, bus factor > 1 per service |
| Regulatory compliance gaps discovered late | Medium | High | Compliance review at each phase gate, external audit at Phase 2 completion |
| Integration with legacy hospital systems (HIS, LIS) | High | Medium | Early discovery of existing systems, HL7/FHIR adapter approach, API-first integration |
| Go-live disruption to hospital operations | Medium | Critical | Phased go-live, parallel run, 24/7 war room during go-live week, instant rollback plan |

# 15. Overall Timeline and Milestones

| Milestone | Target Date | Deliverables | Go/No-Go Criteria |
| --- | --- | --- | --- |
| Project Kickoff | Week 1 | Team onboarded, repos created, infra provisioned | All team members active, dev environment working |
| Infrastructure Ready | Week 4 | K8s cluster, CI/CD, monitoring, shared libs v1.0 | Pipeline green for all repos, monitoring dashboards live |
| Phase 1 Go-Live | Week 16 | Patient, Appointment, OPD, Billing live | UAT passed, performance within SLA, zero critical bugs |
| Phase 2 Go-Live | Week 32 | IPD, ER, Lab, Radiology, Pharmacy, Nursing, OT live | UAT passed, instrument interfaces working, clinical sign-off |
| Phase 3 Go-Live | Week 44 | Inventory, HR, Blood Bank, Dietary live | UAT passed, data migration validated, admin sign-off |
| Phase 4 Go-Live (Full System) | Week 56 | Insurance, Quality, Analytics, Portal, FHIR live | Full regression passed, security audit clean, DR drill successful |
| Hypercare Complete | Week 60 | 30-day post go-live support | Issue backlog under control, SLA met for 30 days |
| Project Handover | Week 62 | Operations runbook, training materials, warranty period | Signed handover and closure documents |

## 15.1 Estimated Effort Summary

| Phase | Duration | Team (avg) | Person-Months | Key Complexity |
| --- | --- | --- | --- | --- |
| Phase 1: Foundation | 4 months | 16 | 64 | Architecture setup, shared libraries, auth, core patient flows |
| Phase 2: Clinical Core | 4 months | 23 | 92 | Clinical workflows, instrument integration, DICOM, real-time nursing |
| Phase 3: Support Services | 3 months | 18 | 54 | Supply chain, payroll, blood bank, cross-module integration |
| Phase 4: Advanced | 3 months | 20 | 60 | Analytics/BI, FHIR interoperability, patient portal, insurance |
| Total | 14 months | ~19 avg | ~270 | 26 microservices, full hospital digitization |

END OF DOCUMENT

Hospital Management ERP - Phase-Wise Implementation Plan v1.0

Prepared by Siance Software | April 2026